## CustomerFacing-RACI-WARP
Task Category | Roles Tasks | CSA | SSP | ATS | SSSP | MSM/ACM | CE | CSAM | Partner Account Manager | Partner CSA | Partner Support Engineer | Partner Managed Services | Cloud Strategy | Workload Owner | Workload Team (AppOps) | Cloud Adoption | Cloud Operations | Cloud Governance | Cloud Platform | Cloud Automation | Cloud Data Management | DevOps Engineer/SRE | SoC | Security Leadership & Strategy | Application security engineer | Platform security engineer | Security Posture & Compliance Management | Security Architecture
Discovery | Identify targeted customers | [5 empty] | CE
Discovery | Create optimization engagement
Discovery | Build Microsoft/Partner teams to prepare for the engagement
Discovery | Review customer's current Advisor Score for initial readiness
Discovery | Determine whether customer wants to work with a third party
Envision | Deliver WAR optimization briefing to the customer and confirm opportunity
Envision | Define the scope of WAR engagement
Envision | Identify key customer business stakeholders
Envision | Identify key customer technical stakeholders
Envision | Deliver WAR knowledge transfer workshop
Validate | Review common Cloud Operating Models
Validate | Determine best alignment model with the key customer stakeholders
Validate | Evaluate WAR delivery alternatives
Validate | Execute Self-Service online WAR assessment
Validate | Perform detailed WAR assessment with the customer
Validate | Deliver WAR knowledge transfer workshop
Validate | Deploy and Update CCO PowerBI Dashboards from GitHub
Commit | Prepare customer presentation using the Customer Report Template
Commit | Deliver cost optimization workshop to the customer to walk through and review recommendations
Commit | Secure commitment from customer to proceed with implementation plan for cost optimization engagement
Commit | Discuss and position additional services for improvement and remediation |  |  |  | AR
Onboard | Leverage WAR and Advisor recommendations to determine gaps and opportunities for WARP integration within a targeted workload
Onboard | Identify DevOps toolchain to integrate with WAR and Advisor recommendations
Onboard | Identify ITSM Change Management platform to integrate with WAR and Advisor recommendations
Onboard | Perform integration with DevOps tools and generate backlog work items
Onboard | Perform integration with ITSM Change Management platform and schedule changes
Onboard | Determine viability of other alternative integration tools for WAR and Advisor recommendations
Onboard | Identify sponsors and business stakeholders for the WAR improvement activities
Onboard | Identify workload owners to drive the workload specific remediation process
Onboard | Review new WAR and Advisor recommendations for the workloads, add them to backlog, and assign them to workload owners
Onboard | Triage the WAR and Advisor recommendations in a weekly standup meeting with the workload team and assign to a specific owner with a planned due date
Onboard | Complete work items and sub tasks
Onboard | Review and reassign work items and sub tasks
Onboard | Report on the progress of WAR and Advisor recommendations and related work items to all stakeholders every quarter (within maximum 90 days)
Onboard | Report Advisor score trends to all stakeholders weekly
Onboard | Confirm completed WAR and Advisor recommendations
Note on N1: Bulent Ozkir: Customer Roles/Personas